## ReadMe
Natural England
Project Name: |  | Exemplar Diffuse Water Pollution Plan
Project Number: |  | 5128377
Document Title: |  | Draft Wensum DWPP Action Table
Document Ref: |  | DG017
Version | Date | Status | Description | Author | Checker | Reviewer | Authorised
1 | 2014-04-17 | Draft | Draft Action Plan | CA | DG | HG | HG
2 | 2014-05-23 | Final | Final Action Plan for the Wensum | CA | DG | HG | HG
Overview
This spreadsheet presents the Actions for the Wensum DWPP
Description of each worksheet
Worksheet Name |  |  | Description
Wensum DWPP_Action_Plan |  |  | This contains the actions for each water body of the Wensum. The action are grouped by Sector or theme (Column C) and also by each water body (columns K to AD) for easy reference.

## Wensum DWPP_Action_Plan
[10 empty] | Tud | Wendling Beck | Blackwater (Wendling Beck) | Swannington Beck | Wensum | Blackwater Drain (Wensum) | Foulsham Tributary | Little Ryburgh Tributary | Tat | Wensum US Norwich | Wensum DS Norwich | Penny Spot Beck | Blackwater Drain | Blackwater Drain | Tributary of Blackwater Drain | Tributary of Wensum | Tributary of Blackwater Drain | Wensum | East Rudham Stream | Tat
Scale / location | Investigation / Advice / Scheme / Regulation | Sector | Action Ref No. | Action Title | Action Description | Pollutant(s) the action will tackle | Type of action/measure | How? | Criteria for WB selection | GB105034051000 | GB105034051020 | GB105034051050 | GB105034051070 | GB105034051110 | GB105034051120 | GB105034055850 | GB105034055860 | GB105034055870 | GB105034055881 | GB105034055882 | GB105034051010 | GB105034051030 | GB105034051040 | GB105034051060 | GB105034051080 | GB105034051090 | GB105034051100 | GB105034051130 | GB105034051140 | Who? | When? | Progress as of xxxx (insert date) | Issues/ effectiveness/ learning points
SSSI catchment | Investigation | Agriculture & Land Management | W_DWPP_001 | Review the existing Agri-Environment implementation | Undertake a review of the extent of Agri-environment measures uptake including: where active engagement has been successful; where resource protection measures have been implemented; what extent of the catchment is taking up resource protection options; are these measures being located in the right places relative to the risk (overlay erosion risk map and agricultural risk map) and where there is a known issue (link to water quality monitoring / SAGIS outputs for load concentrations on a sub-catchment level). This will help identify, at a sub-catchment level, a prioritisation plan that is linked to specific pressures in individual water bodies. | Phosphorus | Evidence investigation & site specific action plan | Natural England - Review of CSF and Agri Environment | All sub-catchments that are under Environmental Stewardship with a particular focus on those that are eligible for Higher Level Stewardship. All sub-catchments currently have a degree of ELS uptake, whereas HLS uptake is more common in the middle section of the overall SSSI catchment | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | N | Y | Y | Y | Y | Y | Y | Y | Y | Y | Natural England
Specific catchments | Scheme | Agriculture & Land Management | W_DWPP_002 | Re-focused agri-environment priorities | Use the outputs W_DWPP_001 (review of existing agri-environment implementation) to implement advice and schemes that are more targeted to phosphate reduction in areas where there is an issue (based on evidence) or higher risk (based on available evidence). | Phosphorus | Scheme | Existing NE Agri-Environment | Water body selection for this measure is dependent on the outcomes of the Agri-environment review (W_DWPP_001) | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | Natural England
SSSI catchment | Advice | Agriculture & Land Management | W_DWPP_003 | DWPP re-focus communication | Following review of Agri-environment implementation and ECSFDI reviews (W_DWPP_001 and W_DWPP_009) communicate any catchment priority changes to land managers and stakeholders, including NE, EA, NFU, CLA, Agronomists etc. | All | Advice | Existing communications routes, farm shows; ECSFDI visits; NE catchment officers, local websites etc. | Communication should be SSSI catchment-wide. | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Natural England
SSSI catchment | Regulatory | Agriculture & Land Management | W_DWPP_004 | NVZ inspections | Higher rate of NVZ inspections to promote better nutrient management planning in high risk sub-catchments or where there is suspected issues with management practices or seasonal high risk activities. | Nitrates primarily but some benefit for phosphorus and sediment through advice and culture change | Monitoring outcomes and compliance | Existing EA mechanism for inspections | All sub-catchments that are within the NVZ boundary (NB: those marked with an N are water bodies that fall outside the NVZ) | Y | Y | Y | N | Y | N | N | Y | Y | Y | Y | N | N | N | N | Y | N | Y | Y | Y | Environment Agency
SSSI catchment | Regulatory | Agriculture & Land Management | W_DWPP_005 | CSF visits | Higher rate of Agri-environment inspections following scheme implementation. This would be focused in target areas where measures being implemented for resource protection are highly site-specific and seasonal. | Phosphorus | Monitoring outcomes and compliance | Existing EA mechanism for inspections | All sub-catchments in the SSSI catchment with the exception of urban dominated catchments (as defined in the CORINE land mapping) | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | N | Y | Y | Y | Y | Y | Y | Y | Y | Y | Natural England / Rural Payments Agency
SSSI catchment | Investigation | Agriculture & Land Management | W_DWPP_006 | Investigation into the feasibility of catchment scale agri-environment schemes | Investigation into the feasibility and land owner / land manager appetite for catchment scale agri-environment schemes, whereby farmers of a specific farm type all sign up to a certain level of measures and all have to comply in order for payments to be received. The idea of this is so that action is wide-spread and simultaneous instead of piecemeal and thus the outcomes may be easier to monitor. | Phosphates, sediment, nitrates, pesticides | Evidence investigation & site specific action plan | ECSFDI / NE Agri-Environment combination and consideration of using DTC / Rivers Trusts and Agronomists for support | All sub-catchments in the SSSI catchment that are under Environmental Stewardship of some description, with the exception of urban dominated catchments | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | N | Y | Y | Y | Y | Y | Y | Y | Y | Y | Natural England, Rivers Trusts, possibly Water Company
Specific catchments | Scheme | Agriculture & Land Management | W_DWPP_007 | Pilot study into catchment scale agri-environment schemes | Following on from W_DWPP_006, trial a pilot catchment-scale agri environment scheme, monitor implementation outcomes | Phosphorus | Pilot scheme | NE local project | TBC (dependent on outcomes of above task) (W_DWPP_006) | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | Natural England, Rivers Trusts, possibly Water Company
SSSI catchment | Scheme | Agriculture & Land Management | W_DWPP_008 | Promotion of best practice | Promote best practice through existing assurance schemes – e.g. Red Tractor | Phosphates, sediment, pesticides, nitrates | Assurance scheme | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | Natural England, NFU, CLA, CFE
SSSI catchment | Investigation | Agriculture & Land Management | W_DWPP_009 | Re-focus of the England Catchment Sensitive Farming Delivery Initiative programme activities within the SSSI catchment | This programme should be re-appraised within the catchment so that it is specifically targeted to locations where the phosphate pressure (identified in the data) or risk (from high-risk activities) is greatest. This could include specific farm types, locations, or locations that are known to be poorly managed, or a combination thereof. | Phosphates | Evidence investigation | ECSFDI | All water bodies within the SSSI catchment that have a strong agricultural pressure should be re-appraised. These water bodies have been identified using SAGIS data and selected because >25% of the phosphate load is estimated to be coming from agricultural sources. | Y | N | Y | Y | Y | N | Y | N | N | Y | Y | Y | N | Y | Y | Y | Y | Y | N | Y | Natural England, Defra
SSSI catchment | Advice and Scheme | Agriculture & Land Management | W_DWPP_010 | Phosphate targeted ECSFDI Implementation | Following on from the appraisal of ECSFDI (W_DWPP_010) pursue a refocused programme of advice and schemes under ECSFDI and NE Agri-advisors to target specific areas within the catchment, delivering targeted advice and capital grants for phosphate-reducing land management practices and infrastructure. | Phosphorus | Advice and Scheme | ECSFDI | TBC (dependent on outcomes of above task) | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | Natural England, Defra
SSSI catchment | Investigation | Rural | W_DWPP_011 | Septic tank risk mapping | Undertake a risk mapping exercise using GIS, sewer network map, and undertake a distance to watercourse assessment to produce risk hot spot map to define areas where the catchment shows elevated phosphate levels coincident with high risk from septic tanks (location and distance to source assessment) and a higher source apportionment attributable to OSWwTSs. | Phosphorus | Evidence investigation | ? | All sub-catchments within the SSSI catchment should be subject to risk mapping in order to understand where the risk is and further targeting etc. | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | N | Y | Y | Y | Y | Y | Y | Y | Y | Y | Environment Agency / Natural England
Specific catchments | Advice | Rural | W_DWPP_012 | Action on poor septic tank management / mis connections | Dependent on the outcomes of W_DWPP_011 Septic tank risk mapping, take action: for example where poor septic tank management is possibly causing an issue, investigate on site on a case by case basis. Alongside this, undertake a communications campaign on good practice management for septic tanks. | Phosphorus | Advice / Regulatory | EA | Catchments selected here have an estimated >200 people not served by mains sewerage (the Tud, Wendling Beck, Swannington Beck, Tributary of Blackwater Drain, Foulsham Tributary and Wensum US Norwich). Further catchment should be added depending on the outcomes of related action (W_DWPP_011) | Y | Y | TBC | Y | TBC | TBC | Y | TBC | TBC | Y | TBC | TBC | TBC | TBC | Y | TBC | TBC | TBC | TBC | TBC | Environment Agency
SSSI catchment | Investigation | Rural | W_DWPP_013 | Road run-off investigations | Undertake a risk mapping exercise using road network, slope and connectivity to water course to understand the relative risks from road run-off. Ground-truth with site visits to verify. | Phosphorus and sediment | Evidence investigation | EA, Local Authority, Highways Agency | All sub-catchments within the SSSI catchment should be subject to risk mapping as this isn't just related to urban or rurally dominated areas and is specific to road network, land use, slope and existing mitigation. | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Environment Agency / Natural England
Specific catchments | Scheme | Rural | W_DWPP_014 | Road run-off pathway disruption techniques | Depending on the outcomes of W_DWPP_013 (Road run off risk mapping and investigations) implement pathway disruption techniques so that roads are not channelling rural run-off directly into water courses. | Phosphorus and sediment | Scheme | EA, Local Authority, Highways Agency | TBC (dependent on outcomes of related task W_DWPP_013) | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | EA, Local Authority, Highways Agency
Specific catchments | Investigations | Urban | W_DWPP_015 | Assessment of SUDS potential within the catchment | Investigation into SUDS potential to reduce urban diffuse run off in certain areas of the catchment where urban pressures are present. | Phosphates, sediment, metals | Evidence investigation | EA guidance to local planning initiatives (for new builds) and EA/NE work with Local Authorities to retro fit SUDS where appropriate | Key focus on water bodies where large (>25%) portion of the source apportionment is attributed to urban. These are marked as Y here as they are considered priorities. | N | N | N | N | N | N | N | Y | Y | N | N | N | N | N | N | Y | N | N | N | Y | Natural England (driving), Environment Agency and Local Authorities / Councils etc
SSSI catchment | Policy review | Agriculture & Land Management | W_DWPP_016 | Review of phosphate-reducing measures available through HLS and ELS | Undertake a policy review and understand the further scope for targeting towards resource protection and re-targeting of HLS priorities and measures if required | Phosphates as primary, with some benefit for nitrates, sediment, pesticides. In some cases, additional benefits for biodiversity. | Evidence investigation | Defra and Natural England | TBC | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Natural England, Defra, Environment Agency
SSSI catchment | Advice | Agriculture & Land Management | W_DWPP_017 | FARMSCOPER 1-2-1s | Farm visits to targeted farms to introduce FARMSCOPER and how it can help plan measures and how much it will cost / save the farmer. This could be prioritised where farmers currently are not engaged or where they are engaged and influential with nearby farms (providing a leading by example type approach). This measure will also provide support to farmers in producing nutrient management plan on a farm level. | Phosphates as primary focus, with some benefit for nitrates, sediment, pesticides. In some cases, additional benefits for biodiversity. | Advice and Scheme | Catchment Sensitive Farming (ECSFDI), Natural England catchment officers and ESS delivery officers | Priority catchments marked here include those where arable or livestock are contributing >25% of phosphate load within the catchment; further prioritisation exercise should be undertaken based on local knowledge, contacts and engagement rates | Y | N | Y | Y | Y | N | Y | N | N | N | N | Y | N | Y | Y | Y | Y | Y | N | Y | Natural England
Specific catchments | Schemes | Agriculture & Land Management | W_DWPP_018 | Engagement with the Rivers Trusts to maximise wider benefits | Working with the Rivers Trusts to review their Catchment Based Approach programme of work to see if there is the potential for multiple-wins, or where key DWPP messages could be delivered through RT-to-farmer engagement. | Phosphates as primary, with some benefit for nitrates, sediment, pesticides. In some cases, additional benefits for biodiversity. | Advice and Scheme | Catchment Based Approach | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | Natural England and Rivers Trusts / Broads Authority
SSSI catchment | Advice | Agriculture & Land Management | W_DWPP_019 | DWPP Communications Plan | Formulate a brief communications plan for the DWPP that targets farm shows and local events to deliver the DWPP message and outcomes. Also engage agronomists to help reinforce the message through their farm contracts. The overall objective of this measure is to spread the DWPP message and encourage farmers to take ownership of the issue and work alongside NE to help solve the problem. | Phosphates as primary, with some benefit for nitrates, sediment, pesticides. In some cases, additional benefits for biodiversity. | Advice delivery | Farm shows / local communication routes | All catchments selected as this isn't an activity that is specifically tied to water bodies. | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Natural England
SSSI catchment | Advice | Agriculture & Land Management | W_DWPP_020 | Delivery of more evidence-based advice to farmers | Work closely with farmers to demonstrate the evidence base and preferred options for mitigation, guiding farmers to more appropriate land management measures. This is aimed at promoting a culture change whereby farmers learn about the evidence base and what can be done about it, which could help promote ownership of the problem and a culture of trust. | Sediment and phosphate | Advice delivery | Catchment Sensitive Farming (ECSFDI), Natural England catchment officers and ESS delivery officers | Priority catchments marked here include those where arable or livestock are contributing >25% of phosphate load within the catchment; further prioritisation exercise should be undertaken based on local knowledge, contacts and engagement rates | Y | N | Y | Y | Y | N | Y | N | N | N | N | Y | N | Y | Y | Y | Y | Y | N | Y | Natural England with support from NFU / CLA / Agronomists
SSSI catchment | Advice | Agriculture & Land Management | W_DWPP_021 | Engagement with local NFU and CLA representatives | Proactive engagement with the local NFU and CLA to present the evidence base and promote a positive relationship. | Sediment and phosphate | Advice delivery | Meetings / presentations | All catchments | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Natural England
SSSI catchment | Monitoring outcomes | Agriculture & Land Management | W_DWPP_022 | Monitoring change in practice | Track change in practice as a result of the action plan and produce an update report through future iterations of the DWPP. | All | Monitoring outcomes and compliance | Through future iterations of the action plan | All catchments | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Natural England | Bi-annual update
SSSI catchment | Investigation | Agriculture & Land Management | W_DWPP_023 | Bank erosion investigation | Investigation into sources of phosphate /sediment from bank erosion (as identified by SEPARATE model) through targeted catchment walkovers | Sediment and phosphate | Evidence investigation | Catchment Sensitive Farming (ECSFDI), Natural England catchment officers and ESS delivery officers | Priority catchments marked here include those where arable or livestock are contributing >25% of phosphate load within the catchment | Y | N | Y | Y | Y | N | Y | N | N | N | N | Y | N | Y | Y | Y | Y | Y | N | Y | Natural England / Environment Agency
Specific catchments | Advice / Schemes: Arable – General cropping | Agriculture & Land Management | W_DWPP_024 | Arable farming measures for General Cropping farm types - promotion of the "top 5" measures | Liaise with farmers within the high priority areas to push top 5 measures for phosphorus reductions on this farm type: 4 - Establish cover crops in the autumn; 8 - Cultivate compacted tillage soils; 9 - Cultivate and drill across the slope; 13 - Establish in-field grass buffer strips; 15 - Loosen compacted soil layers in grassland fields | Phosphates as primary, with some benefit for nitrates, sediment, pesticides. In some cases, additional benefits for biodiversity. | Advice delivery and schemes | CSF / NE Agri-Environment combination | All general cropping holdings should eventually be targeted however the priorities set out here are for water bodies that show >25% of phosphate load from arable sector and / or for which the agri census data shows a high proportion of general cropping (>10 holdings in the water body) | Y | Y | N | Y | N | Y | N | N | Y | N | N | N | N | N | N | N | N | N | N | Y | NE and landowners
Specific catchments | Advice / Schemes | Agriculture & Land Management | W_DWPP_025 | Arable farming measures for Cereals farm types - promotion of the "top 5" measures | Liaise with farmers within the high priority areas to push top 5 measures for phosphorus reductions on this farm type: 4 - Establish cover crops in the autumn; 8 - Cultivate compacted tillage soils; 9 - Cultivate and drill across the slope; 13 - Establish in-field grass buffer strips; 15 - Loosen compacted soil layers in grassland fields; 106 - Plant areas of farm with wild bird seed / nectar flower mixtures | Phosphates as primary, with some benefit for nitrates, sediment, pesticides. In some cases, additional benefits for biodiversity. | Advice delivery and schemes | CSF / NE Agri-Environment combination | All cereal holdings should eventually be targeted however the priorities set out here are for Prioritise implementation in water bodies that show >25% of phosphate load from arable sector and / or for which the agri census data shows a high proportion (>10 holdings) of cereal holdings within the water body. | Y | Y | Y | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N | NE and landowners
Specific catchments | Advice / Schemes: Livestock – Lowland grazing | Agriculture & Land Management | W_DWPP_026 | Livestock farming measures for Lowland grazing farm type - promotion of the "top 5" measures. | Liaise with farmers within the high priority areas to push top 5 measures for phosphorus reductions on this farm type: 76 - Fence off rivers and streams from livestock; 35 - Reduce the length of the grazing day/grazing season; 61 - Store solid manure heaps on an impermeable base and collect effluent; 78 - Re-site gateways away from high-risk areas; 39 - Construct troughs with concrete base | Phosphates as primary, with some benefit for nitrates, sediment, pesticides. In some cases, additional benefits for biodiversity. | Advice delivery and schemes | CSF / NE Agri-Environment combination | All livestock farms should eventually be targeted, however the priorities set here are for water bodies that show >25% of phosphate load from livestock and / or for which the agri census data shows a high number of lowland grazing farms (>10 holdings in water body) | Y | N | Y | Y | N | N | Y | N | N | N | N | Y | N | Y | Y | N | Y | N | N | N | NE and landowners
Specific catchments | Advice / Schemes: Livestock – Mixed grazing | Agriculture & Land Management | W_DWPP_027 | Livestock farming measures for Mixed grazing farm type - promotion of the "top 5" measures. | Liaise with farmers within the high priority areas to push top 5 measures for phosphorus reductions on this farm type: 35 - Reduce the length of the grazing day/grazing season; 60 - Site solid manure heaps away from watercourses/field drains; 61 - Store solid manure heaps on an impermeable base and collect effluent; 62 - Cover solid manure stores with sheeting; 39 - Construct troughs with concrete base | Phosphates as primary, with some benefit for nitrates, sediment, pesticides. In some cases, additional benefits for biodiversity. | Advice delivery and schemes | CSF / NE Agri-Environment combination | All livestock farms should eventually be targeted, however the priorities set here are for water bodies that show >25% of phosphate load from livestock and / or for which the agri census data shows a high number of mixed grazing farms (>10 holdings in water body) | Y | N | Y | Y | N | N | N | N | N | N | N | Y | N | Y | Y | N | Y | N | N | N | NE and landowners
Specific catchments | Advice / Schemes: Specialist farming – Specialist pigs | Agriculture & Land Management | W_DWPP_028 | Specialist pig farming measures - promotion of the "top 5" measures: | Liaise with farmers within the high priority areas to push top 5 measures for phosphorus reductions on this farm type: 8 - Cultivate compacted tillage soils; 13 - Establish in-field grass buffer strips; 15 - Loosen compacted soil layers in grassland fields; 78 - Re-site gateways away from high-risk areas; 106 - Plant areas of farm with wild bird seed / nectar flower mixtures | Phosphates as primary, with some benefit for nitrates, sediment, pesticides. In some cases, additional benefits for biodiversity. | Advice delivery and schemes | CSF / NE Agri-Environment combination | Prioritise sub-catchments with pig farms (Tud, Wendling Beck and Tat, confirmed by agri-census statistics) as a starter but investigate the degree of suppressed data in the Little Ryburgh and Swannington sub-catchments as these may also contain pig farms | Y | Y | N | TBC | N | N | N | TBC | Y | N | N | N | N | N | N | N | N | N | N | Y | NE and landowners
Specific catchments | Advice / Schemes: Specialist farming – Specialist poultry | Agriculture & Land Management | W_DWPP_029 | Specialist poultry farming measures - promotion of the "top 5" measures: | Liaise with farmers within the high priority areas to push top 5 measures for phosphorus reductions on this farm type: 34 - Adopt phase feeding of livestock; 38 - Move feeders at regular intervals; 78 - Re-site gateways away from high-risk areas; 106 - Plant areas of farm with wild bird seed / nectar flower mixtures; 332 - Reduce dietary N and P intakes: Pigs and Poultry | Phosphates as primary, with some benefit for nitrates, sediment, pesticides. In some cases, additional benefits for biodiversity. | Advice delivery and schemes | CSF / NE Agri-Environment combination | Target licence poultry farms within the catchment - Tud, Wensum (to Tatterford) and Wensum US Norwich as a starter but also investigate the degree of suppressed data in Little Ryburgh and Tat catchments. | Y | N | N | N | Y | N | N | TBC | N | Y | N | N | N | N | N | Y | N | Y | N | TBC | NE and landowners
Specific catchments | Investigation | Water Industry | W_DWPP_030 | Water Company investigations to reduce phosphorus in discharges | EA and Water Company to investigate potential for reducing phosphorus in wastewater discharges in selected catchments. This could be approached either through improving existing operations or through new infrastructure, although consideration could also be given to catchment management approaches as an alternative, where suitable. | Phosphorus | Investigation / regulatory mechanism | Water Company planning cycle / NEP | Action (in the form of investigations) prioritised here in water bodies where >25% of phosphate load is attributed to STW. However, a catchment wide investigation should be undertaken on the current phosphate consent, level of treatment and potential for improvements. | Y | Y | N | Y | N | Y | N | N | N | N | N | N | Y | Y | N | N | N | N | Y | N | NE and landowners | 2015
Specific catchments | Investigation / regulatory mechanism | Agriculture & Land Management | W_DWPP_032 | Unconsented farm discharges | Identify unconsented discharges from farms, for example specific farms with poor management practice e.g. Slurry pit / field corner management etc. If the issue is significant then identify approporiate ways to tackle the issue. | Phosphorus | Investigation / regulatory mechanism | EA pollution inspection procedure | Investigations in all agriculturally dominated catchments | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | N | Y | Y | Y | Y | Y | Y | Y | Y | Y | Environment Agency
Specific catchments | Investigation / regulatory mechanism | Urban | W_DWPP_033 | Unconsented urban discharges | Identify and remedy unconsented discharges from the urban environment, for example e.g. misconnections etc | Phosphorus | Investigation / regulatory mechanism | EA pollution inspection procedure | Specific catchments where urban is responsible for significant (>25%) portion of the phosphate load, and / or intermittents sources have been identified in the SAGIS model | Y | Y | N | N | N | N | N | Y | Y | N | N | N | N | N | N | Y | N | N | N | Y | Environment Agency
Specific catchments | Investigation / regulatory mechanism | Industry | W_DWPP_034 | Unconsented industrial discharges | Identify and remedy unconsented industrial discharges for example from small industrial estates or industrial areas | Phosphorus | Investigation / regulatory mechanism | EA pollution inspection procedure | Specific catchments where land use data (CORINE) shows industrial land use. Tat, Blackwater (Wendling Beck) Tud. | Y | N | Y | N | N | N | N | N | Y | N | N | N | N | N | N | N | N | N | N | N | Environment Agency
Specific catchments | Investigation | Agriculture & Land Management | W_DWPP_035 | Adding to the evidence base | Address knowledge gap for sediment to improve evidence base for sediment: · Collate information to generate baseline of information of sediment pressures for the SSSI · Undertake mapping exercises to identify reaches that suffer from deposited sediment · Identify any literature studies that quantify sediment movement · Commission assessments in water bodies that have data gaps or uncertainties | Sediment | Investigation / regulatory mechanism | Commission of surveys, and data collection | Data collection in specific water bodies that have information gaps or uncertainties | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Natural England, Environment Agency